## Sheet1
Date | Task | Duration | Status | Meeting Description | Link | Comments
2022-05-20 | GSoC 22 Result Declared !!
2022-05-21 | Task 1 - Set up a quick meeting with mentor (JN) Task 2 - Set up git repo and added JN |  |  | Meeting with nashjc - 1) Discussed communications (email and Google Meet) 2) Set up StochOptim repo and gave nashjc access
2022-05-22
2022-05-23
2022-05-24
2022-05-25 | EXAM
2022-05-26
2022-05-27
2022-05-28
2022-05-29
2022-05-30 | Task 1 - make a quick prototype and get approval Task 2 - read prof. Cortez's book to get some understanding (i am clueless right now) Task 3 - understand Git and Github | Meeting ~ 1 hour | Done | Meeting (JCN, HWB, PC) - 1. Solver selection (pso,GenSA,DeOptimR,GA,ecr) 2. Calling hierarchy (local wrapper + global wrapper) 3. Different configuration of control list | 1. Github for Rstudio 2. Prof. Cortez book | Found resources - Data Science and R
2022-05-31 | Task 1 - Read Advanced Object-Oriented Programming in R Task 2 - can StochOptim problem be modeled as object oriented system ? Task 3 - S3 vs S4 vs R6 systems in R |  | Done |  |  | 1. Object oriented programming in R blog 2. Object oriented programming in R paper
2022-06-01 | Task 1 - ask the mentor (ncj) for a quick meeting to understand the problem once more from the user's pespective Task 2 - write some code using S3 system and also maybe using R6 system to compare them |  | Done
2022-06-02 | Task 1 - utterly wasted time understanding and implementing things using S3 Task 2 - started understanding and reading about R6 |  | Done
2022-06-03 | Task 1 - write a prototype implementation using R6 Task 2 - write a mail explaining the idea to mentors Task 3 - analyse their feedback, give replies and correct few things |  | Done
2022-06-04 | Task 1 - find a better place to discuss things (mail dosen't wrok well for detailed conversations) Task 2 - implement checks on parameters for DEoptim |  | Done |  | 1. Github issues
2022-06-05 | Task 1 - make UML digrams namly class digram, sequence digram, and usecase digram |  | Pending
2022-06-06 | Task 1 - reorganise files and make a package Task 2 - make a optimizerwrapper class which will be inhereted by "specific" optimizer wrapper class. Task 3 - make a LocalWrapper class |  | Done |  |  | I did think that making local wrapper as a class would be a a good idea but now am not too sure (11 june 2022)
2022-06-07 | Task 1 - add pso and GenSA optimizer Task 2 - reorganise file as a script first (package pending) |  | Done
2022-06-08 | Task 1 - fixed upper / lower cases in file and function names |  | Done
2022-06-09 | Task 1 - created new disscussion regarding coding style and naming conventions |  | Done
2022-06-10 | Task 1 - creating package from prototype |  | Done
2022-06-11 | Task 1 - wrote code to add new solver as an answer to the question asked by prof. Werner |  | Done
2022-06-12
2022-06-13 | Task 1 - add ecr |  | Pending
2022-06-14 | Task 1 - add DroptimR |  | Done
2022-06-15 | Task 1 - add adagio simpleDE Task 2 - changed the file and function names Task 3 - tried to solve ecr issue (it's confusing me) |  | Done
2022-06-16 | Task 1 - resolved warning and notes that appear with R CMD check (having some back and forth with college authority) |  | Done
2022-06-17 | Task 1 - solve R CMD Check warning on windows machine. Task 2 - started adding global options /controls |  | in progress | Meeting with nashjc - 1. discussion about trace levels 2. posibility of having different versions of same optimizer 3. discussion on global and local/specific control options 4. discussion on how to pass optimizer specific controls in sopm
2022-06-18