## Sheet1
Date | Task | Duration | Status | Meeting Description | Link | Comments
2022-05-20 | GSoC 22 Result Declared !!
2022-05-21 | Task 1 - Set up a quick meeting with mentor (JN) Task 2 - Set up git repo and added JN |  |  | Meeting with nashjc - 1) Discussed communications (email and Google Meet) 2) Set up StochOptim repo and gave nashjc access
2022-05-22
2022-05-23
2022-05-24
2022-05-25 | EXAM
2022-05-26
2022-05-27
2022-05-28
2022-05-29
2022-05-30 | Task 1 - make a quick prototype and get approval Task 2 - read prof. Cortez's book to get some understanding (i am clueless right now) Task 3 - understand Git and Github | Meeting ~ 1 hour | Done | Meeting (JCN, HWB, PC) - 1. Solver selection (pso,GenSA,DeOptimR,GA,ecr) 2. Calling hierarchy (local wrapper + global wrapper) 3. Different configuration of control list | 1. Github for Rstudio 2. Prof. Cortez book | Found resources - Data Science and R
2022-05-31 | Task 1 - Read Advanced Object-Oriented Programming in R Task 2 - can StochOptim problem be modeled as object oriented system ? Task 3 - S3 vs S4 vs R6 systems in R |  | Done |  |  | 1. Object oriented programming in R blog 2. Object oriented programming in R paper
2022-06-01 | Task 1 - ask the mentor (ncj) for a quick meeting to understand the problem once more from the user's pespective Task 2 - write some code using S3 system and also maybe using R6 system to compare them |  | Done
2022-06-02 | Task 1 - utterly wasted time understanding and implementing things using S3 Task 2 - started understanding and reading about R6 |  | Done
2022-06-03 | Task 1 - write a prototype implementation using R6 Task 2 - write a mail explaining the idea to mentors Task 3 - analyse their feedback, give replies and correct few things |  | Done
2022-06-04 | Task 1 - find a better place to discuss things (mail dosen't wrok well for detailed conversations) Task 2 - implement checks on parameters for DEoptim |  | Done |  | 1. Github issues
2022-06-05 | Task 1 - make UML digrams namly class digram, sequence digram, and usecase digram |  | Pending
2022-06-06 | Task 1 - reorganise files and make a package Task 2 - make a optimizerwrapper class which will be inhereted by "specific" optimizer wrapper class. Task 3 - make a LocalWrapper class |  | Done |  |  | I did think that making local wrapper as a class would be a a good idea but now am not too sure (11 june 2022)
2022-06-07 | Task 1 - add pso and GenSA optimizer Task 2 - reorganise file as a script first (package pending) |  | Done
2022-06-08 | Task 1 - fixed upper / lower cases in file and function names |  | Done
2022-06-09 | Task 1 - created new disscussion regarding coding style and naming conventions |  | Done
2022-06-10 | Task 1 - creating package from prototype |  | Done
2022-06-11 | Task 1 - wrote code to add new solver as an answer to the question asked by prof. Werner |  | Done
2022-06-12
2022-06-13 | Task 1 - add ecr |  | Pending
2022-06-14 | Task 1 - add DroptimR |  | Done
2022-06-15 | Task 1 - add adagio simpleDE Task 2 - changed the file and function names Task 3 - tried to solve ecr issue (it's confusing me) |  | Done
16 June Thu | lost work on ecr |  | Done |  |  | My Windows machine keeps crashing for no reason
17 June Fri | Task 1 - solve R CMD Check warning on windows machine. (still not completely gone) Task 2 - errors of linux machine were solved Task 3 - started adding global options /controls |  | Done | Meeting with nashjc - 1. discussion about trace levels 2. posibility of having different versions of same optimizer 3. discussion on global and local/specific control options 4. discussion on how to pass optimizer specific controls in sopm
18 June Sat | Task 1 - found a better method to implement global options using :- vcontrol = c (popsize = "NP") # DEoptim Task 1 - added global options to DEoptim , adagio simpleDE |  | Done |  |  | The example is of DEoptim
19 June Sun |  |  | Done | Meeting nashjc - 1) code review 2) advice on documentation 3) Ideas for sopm |  | Meeting went well, my implmentation got a go ahead.
20 June Mon | Task 1 - added global to pso and GenSA Task 2 - started documentation of classes and function |  | Done
21 June Tue | Task 1 - added sopm function Task 2 - update pakage with new version of R Task 3 - resolve all the windows related error |  | Done
22 June Wed | Task 1 - implemented global control for all the optimizers |  | Done
23 June Thu | Task 1 - documentation Task 2 - trace translation |  | Done
24 June Fri | Task 1 - time diff for solvers |  | Done
25 June Sat | Task 1 - refered to chapter 12 R package (unit test) Task 2 - simple tests for method and functions |  | Done
26 June Sun
27 June Mon | Task 1 - Fix problem in sopm Task 2 - combine checkcontrol() and controltranslation() in one procedure |  | Done | Meeting with nashjc -
28 June Tue
29 June Wed
30 June Thu
1 July Fri | Task 1 - fixed a error with pso (all other Solvers were workin fine but not pso) Task 2 - implemented nested control list structure in sopm |  | Done
2 July Sat | Task 1 - creared tests to see if all the optimizer Work |  | Done
3 July Sun | Task 1 - fixed the issues with test cases |  | Done | Meeting with nashjc -
4 July Mon | Task 1 - reorganised the code. Task 2 – started working on ecr |  | Done
5 July Tue | Task 1 – found a temp fix for ecr Task 2 – got ecr working (not the correct way) |  | Done
6 July Wed | Task 1 – added test case for ecr Task 2 – removed hard coded print values from the code |  | Done
7 July Thu | Task 1 – started working on documentation by Giving a description of internal working of the package |  | Done
8 July Fri | Task 1 – added instruction to add new solvers |  | Done
9 July Sat | Task 1 – added ellipsis or three dot (...) operator To all the optimizers except adagio since it dosen’t support it. Task 2 – added many improvements to sopm Task 3 – added trace control for Deoptim |  | Done
10 July Sun | Task 1 – fixed the sopm error which happpend while adding trace control for Deoptim Task 2 – added test cases to check if extra parameter to objective function work Task 3 – added default trace to DEoptim |  | Done
11 July Mon | Task 1 – updating vignette Task 2 – adding trace control for pso |  | in progress
12 July Tue | Task 1 – adding test for check if trace works Works for Deoptim
13 July Wed